## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Research
1.1 | Topic Research |  | 2019-05-14 | 2019-05-15 | 1 | 100%
1.2 | Search apps that are similar |  | 2019-05-15 | 2019-05-16 | 1 | 100%
1.3 | Scope, MOV, Objectives |  | 2019-05-15 | 2019-05-16 | 1 | 100%
1.4 | Consult advisors |  | 2019-05-16 | 2019-05-16 | 0 | 100%
2 | Project Planning
2.1 | Review research proposal |  | 2019-05-20 | 2019-05-21 | 1 | 100%
2.2 | Risk Management |  | 2019-05-21 | 2019-05-22 | 1 | 100%
2.3 | Selection of Tools |  | 2019-05-22 | 2019-05-22 | 0 | 100%
2.4 | Consult advisors |  | 2019-05-23 | 2019-05-23 | 0 | 100%
3 | Design
3.1 | Prototype Design |  | 2019-06-03 | 2019-06-06 | 3 | 100%
3.2 | Use case and flow charts |  | 2019-06-06 | 2019-06-07 | 1 | 100%
3.2.1 | Consult advisors |  | 2019-06-11 | 2019-06-11 | 0 | 100%
4 | Implementation
4.1 | Programming |  | 2019-06-07 | 2019-06-21 | 14 | 100%
4.2 | Final Testing |  | 2019-06-22 | 2019-06-23 | 1 | 100%
4.3 | Documentation |  | 2019-06-24 | 2019-06-24 | 0 | 100%
5 | Evaluation
5.1 | Review tasks |  | 2019-06-25 | 2019-06-25 | 0 | 100%
5.2 | Improvements/Changes |  | 2019-06-25 | 2019-06-26 | 1 | 100%
5.3 |  |  |  |  | 0 | 0%
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])